## Sheet1
Est End dat | 0 |  | Hard End date | May 02 2025 | Project X - Automated Attendance System
DEADLINE: MAY 02, 2025 | [5 empty] | Days Left: 24 days |  |  |  | Task Done: 8 / 16
Task ID | Task Name | Sub Task ID | SubTask Name | Deliverables | Assignee | Estimated Hours (days) | Pln St Date | Act StDate Started | Pln End Date | Act End Date | Status
1 | Project Initiation | 1.1 | Project Kickoff Meeting |  | JOSEPH | 2 | 2025-03-02 | 2025-03-02 | 2025-03-04 | 2025-03-04 | Done
|  | 1.2 | Identifying Project Scope & Objectives | Updated Requirements Review | HAZELLE | 2 | 2025-03-05 | 2025-03-05 | 2025-03-07 | 2025-03-07 | Done
2 | Requirement Analysis | 2.1 | Gather Functional Requirement | Project X - Client Stated Requirement | NOFAH | 2 | 2025-03-08 | 2025-03-08 | 2025-03-10 | 2025-03-08 | Done
|  | 2.2 | Initiate an Elicitation Session with Client | Project X - Requirements Elicitation - v.1.0 | JOSEPH | 1 | 2025-03-11 | 2025-03-11 | 2025-03-12 | 2025-03-10 | Done
|  | 2.3 | Validate Requirements with Client | Project X - Requirements Elicitation - v.1.1 | HAZELLE | 1 | 2025-03-13 | 2025-03-13 | 2025-03-14 | 2025-03-12 | Done
|  | 2.4 | Finalizing System Requirements | Project X - Requirements Elicitation - v.1.2 | NOFAH | 1 | 2025-03-15 | 2025-03-15 | 2025-03-16 | 2025-03-14 | Done
3 | High-Level Design | 3.1 | Conceptual Design | High-Level Use Case Diagrams, Conceptual Model Requirement Diagrams Project Plan | HAZELLE | 3 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-18 | Done
|  | 3.2 | Revised Deliverables | Project Plan Traceability Matrix | NOFAH | 1 | 2025-03-21 | 2025-03-21 | 2025-03-22 | 2025-03-21 | Done
4 | Detailed Design | 4.1 | Develop Class Diagram | Class Diagram with Attributes & Methods |  | 4 | 2025-03-23 | 2025-03-23 | 2025-03-27 |  | Ongoing
|  | 4.2 | Sequence Diagram | Detailed Sequence Diagram |  | 5 | 2025-03-28 | 2025-03-28 | 2025-04-02 |  | Ongoing
|  | 4.3 | Activity Diagram | Activity Diagrams for Key System Processes |  | 4 | 2025-04-03 | 2025-04-03 | 2025-04-07 |  | Ongoing
|  | 4.4 | Prototyping | Figma Link |  | 3 | 2025-04-08 | 2025-04-08 | 2025-04-11 |  | Ongoing
5 | Documentation & Version Control | 5 | Set up Version Control (Git) | Git Repository Setup Provide Access to Repository |  | 2 | 2025-04-12 | 2025-04-12 | 2025-04-14 |  | Ongoing
6 | Agile Development Process | 6.1 | Sprint Planning | Sprint Backlog Development Roadmap |  | 1 | 2025-04-15 |  | 2025-04-16 |  | Pending
|  | 6.2 | Daily Standups | Recording Progress Updates |  | 2 | 2025-04-17 |  | 2025-04-19 |  | Pending
|  | 6.3 | Sprint Demonstration to Client | Sprint Review, Working Feature Demostration |  | 5 | 2025-04-20 |  | 2025-04-25
7 | Test-Driven Development (TDD) | 7 | Develop & Test a Module using TDD | Test Cases, Unit Tests TDD Implementation |  | 1 | 2025-04-26 |  | 2025-04-27
8 | Implementation | 8.1 | Develop Authentication | Secure API, OTP Authentication, QR Validation |  | 7 | 2025-04-28 |  | 2025-05-05
|  | 8.2 | Implement Role-based Access Control | Admin, Instructor, Student Access System |  | 2 | 2025-05-06 |  | 2025-05-08
|  | 8.3 | Attendance Tracking Features | QR Code Scanner, GPS Validation |  | 5 | 2025-05-09 |  | 2025-05-14
|  | 8.4 | Cloud Database Integration | Hosted Database, Secure APIs |  | 5 | 2025-05-15 |  | 2025-05-20
9 | Testing & Validation | 9.1 | Unit Testing | Verified Functionality of Individual Components |  | 15 | 2025-05-21 |  | 2025-06-05
|  | 9.2 | System Testing | Full System Integration Test |  | 50 | 2025-06-06 |  | 2025-07-26
|  | 9.3 | User Acceptance Testing (UAT) | Client Validation & Feedback |  | 15 | 2025-07-27 |  | 2025-08-11
10 | Final Demonstration & Handover | 10.1 | Final System Review | Working Code, Documentation, User Manual |  | 8 | 2025-08-12 |  | 2025-08-20
|  | 10.2 | Final Presentation | Project Presentation, Live Demo |  | 4 | 2025-08-21 |  | 2025-08-25
Formulas:
Pln End Date = [Estimated Hours (days)] + [Pln St Date]
Pln St Date = [Pln St Date, row above]+[Estimated Hours (days), row above] + 1
Act StDate Started = [Pln St Date, row above]+[Estimated Hours (days), row above] + 1